## Prevention
All-age exploitation strategy 2026/31 - work plan
Priority 1: Prevention
Action No. | Action | Timescale | Lead | Success measure | Outcome | Year
General
1.1 | Establish and maintain a multi-agency exploitation stakeholder network and ensure Brackell Forest is representated at national and regional networks to support collaboration, information-sharing and shared learning. | Year 1 Identify national and regional networks. Identify representation to attend and bring back learning and awareness. | BFC Community Safety Serious Violence and Exploitation Sub-Group of the CSP and BFSB | Networks identified and representation at meetings arranged with regular attendance. | Shared understanding, expertise and good practice. | 1
1.2 | Deliver co-ordinated general public awareness (including national campaigns) as well as targeted awareness activity for communities and groups at increased risk of exploitation using accessible, trauma-informed, culturally sensitive and inclusive messaging to help with understanding exploitation, recognising warning signs and how to seek help through safe and confidential reporting routes for: - children - children approaching adulthood/young adults - adults - professionals - residents - businesses | Year 1 Identification of the groups to target. Research national and regional awareness events. Research existing materials and resources. | Communication sub-group of the BFSB in conjunction with partners | An increase in referrals and reports. Targeted campaigns delivered. | The community are informed and able to identify concerns early, supporting eralier intervention and community vigilance. Prevention messaging is consistent, credible and reinforced across the borough, strengthening public understanding and trust. Individuals feel more confident and reassured when raising concerns, leading to increased and timelier reporting. Vulnerable people and communities are better able to recognise risk and access support before harm escalates. Businesses are better equipped to identify concerns and take responsible action to prevention exploitation. | 1
1.3 | Develop targeted early-intervention trauma-informed pathways specifically for boys and young men as well as girls and young women displaying harmful attitudes or risk factors linked to exploitation or are at risk of being drawn into exploitation networks. | Year 1 Establish and operationalise a multi-agency trauma-informed pathway, with at least 60% of the identified at-risk cohort engaged in an intervention within 4 weeks of identification. | SVE Strategic Sub-Group of the CSP and BFSB | % reduction in identified children and young adults progressing from 'at risk' to 'exploited' or 'exploiter' (as recorded through multi-agency safeguarding data). | Children and young adults at risk of exploitation demonstrate increased protective factors and reduced harmful attitudes/behaviours. | 1
1.4 | Engage community and faith leaders as trusted partners in prevention, awareness and early support activity. | Year 1 Identify key faith/community groups and leaders by linking to local exploitation risks and vulnerable groups. | SVE Strategic Sub-Group of the CSP and BFSB | Number of groups engaged. | Identified trusted leaders/champions for prevention and early support | 1
1.5 | Develop and regularly review a local exploitation profile drawing on multi-agency data and intelligence. | Year 1 Identify sources and nature of data which can be shared and used to steer the work plan. | TVP BFC Makesafe BFC Community Safety | Profile produced on a regular basis and reviewed and discussed routinely to inform work. | Prevention and response activity is informed by robust local evidence and emerging trends. | 1
1.6 | Deliver regular training for community-facing professionals to strengthen understanding of exploitation, trauma and safeguarding responsibilities. | Year 1 Identify suitable and appropriate cross-sector and cross-organisational training as well as sector-specific training. Establish resources to fund training if required. |  | Number of professionals trained. Evaluation of impact of training on practice. | Professionals respond more confidently, consistently and appropriately to concerns. | 1
1.7 | Share information and intelligence-sharing routes between partners, including clear thresholds and feedback mechanisms. | Year 1 Clarify correct and up-to-date intelligence forms and submission details. Identify best ways to share this with all front-line professionals and to ensure that it is held in a location that is easy to find and access. | TVP BFC Community Safety | Increased partner reporting of intelligence. Earlier response to suspected victims and prevention of further harm. | Intelligence forms shared with appropriate front-line teams in BFC and partner organisations. | 1
1.8 | Strengthen contextual safeguarding approaches in identified hotspots through environmental assessments, partnership action and protective measures. | Year 1 Re-publicise the PPSGs to all exploitation prevention stakeholders with clear group objectives, principles and referral process. | CSP Partnership Problem-Solving Groups (PPSGs) and task and finish groups | Multi-partnership target-hardening to reduce risk and threat of exploitation at locations. Safer communities. | Number of referrals to the PPSGs resolved. | 1
1.9 | Share guidance on the Modern Slavery Act and ethical employment practices with employers and partners. | Year 2 Establish appropriate guidance and local networks to share through. | SVE Strategic Sub-Group of the CSP and BFSB | Improved compliance with employment standards and reduced risk of labour exploitation. | Improved compliance and reduced risk of exploitation across the supply chain. | 2
1.1 | Involve people with lived experience, where safe and appropriate, to inform prevention messaging, learning and service improvement. | Year 2/Year 3 Consider sharing an update on the work plan with people with lived experience to gain their views on our progress and explore any further suggestions that can guide our prevention work. | BFC Community Safety BFC Makesafe BFC Youth Services BFC Education BFC Leaving Care | Messaging and approaches are more authentic, sensitive and impactful, reflecting real experiences. | Number of people with lived experience involved. | 2
Cross-border
1.11 | Strengthen cross-border information sharing and intelligence coordination. | Year 1 Explore multi-agency information-sharing protocols with neighbouring areas and police. Ensure consistent recording and flagging of cross-border exploitation risks across systems. | BFC Children's Services - safeguarding lead BFC Adult Services - safeguarding lead TVP - safeguarding/exploitation lead | % of cross-border cases with timely information shared in line with protocol. | Earlier identification and disruption of cross-border exploitation. | 1
1.12 | Improve exploitation risk assessment and safeguarding oversight of all placements (in and out of area). | Year 1 Introduce standardised exploitation risk assessments for all out-of-area placements. Implement notification and review processes for children placed in-borough by other authorities. | BFC Children's Services | % of placements (in and out of area) with completed and reviewed exploitation risk assessments. | Reduced vulnerability linked to unsafe or poorly monitored placements. | 1
1.13 | Strengthen multi-agency oversight and tracking of cross-border and mobile exploitation risk. | Year 1 Embed cross-border exploitation within multi-agency panels (MACE and SAVE). Monitor patterns of movement, missing episodes, and links across areas. | MACE Chair SAVE Chair | % of high-risk cross-border cases reviewed through multi-agency processes. | Improved coordination and earlier intervention for high-risk individuals. | 1
1.14 | Target prevention, outreach, and disruption activity in locations linked to cross-border exploitation. | Use data to identify hotspots linked to cross-border exploitation (e.g. transport hubs, hotels). Deliver targeted outreach, awareness, and disruption activity in those locations. | BFC Community Safety Serious Violence and Exploitation Sub-Group of the CSP and BFSB | Number of targeted operations/interventions delivered in identified hotspots. | Reduced opportunities for exploitation in key locations. | 1
1.15 | Increase workforce, provider, and community awareness of cross-border exploitation risks and responsibilities. | Year 1 Identify training on cross-border exploitation risks, including for care providers and relevant businesses. Promote clear reporting pathways and safeguarding responsibilities. | BFC Community Safety Serious Violence and Exploitation Sub-Group of the CSP and BFSB | % of relevant workforce and partners trained. | Increased identification and reporting of cross-border exploitation risks. | 1

## Transition to Adulthood
All-age exploitation strategy 2026/31 - work plan
Priority 2: Transition into adulthood
M
Action No. | Action | Timescale | Lead | Success measure | Outcome | Year
2.1 | Develop and embed an all-age safeguarding model aligning children’s and adult services, with shared thresholds, governance and accountability. | Year 1 Bring together children’s and adults’ safeguarding leads to align definitions, risk thresholds, and exploitation typologies. | Transition to Adulthood Sub-Group of the BFSB BFC Children's Services - safeguarding lead BFC Adult Services | Multi-agency sign-off of the shared threshold document. | Young people experience continuity of safeguarding support, reducing risks associated with transition to adulthood. | 1
2.2 | Provide personalised transition support beginning well before age 18, with consistent lead professionals and co-produced plans. | Ongoing | Transition to Adulthood Sub-Group of the BFSB BFC Children's Services | % of identified young people with a co-produced transition plan in place by age 16–17. | Young people at risk of exploitation have personalised, co-produced transition plans that continue seamlessly into adult services, reducing disruption and risk at age 18. | N/A
2.3 | Strengthen aftercare pathways for care leavers by embedding exploitation awareness and access to specialist support. | Year 1 Map current leaving care services and aftercare pathways. | Transition to Adulthood Sub-Group of the BFSB BFC Life Chances | % of care leavers with pathway plans including exploitation risk and support actions. | Care leavers receive consistent, exploitation-informed aftercare support, improving safety and stability into adulthood. | 1
2.4 | Explore structured mentoring programmes providing trusted adult relationships and positive role modelling. | Year 1 Investigate and map existing mentoring programmes. | Transition to Adulthood Sub-Group of the BFSB SVE Strategic Sub-Group of the CSP and BFSB | Participant retention and engagement rates in the programme. | At-risk individuals have reliable, positive adult relationships that support resilience, reduce isolation, and lower exploitation risk. | 2
2.5 | Ensure access to education, training and employment by addressing practical, emotional and structural barriers. | Year 1 Assess local education, training, and employment provision to identify gaps and barriers for those affected by exploitation (e.g. stigma, criminal records, disrupted education, immigration status). | Transition to Adulthood Sub-Group of the BFSB Education providers Department for Work and Pensions Probation and Youth Justice Services Voluntary and community sector organisations | Increased number of individuals entering and sustaining education, training, or employment, alongside improved confidence and stability reported by service users. | Individuals affected by exploitation are supported to access and sustain education, training, or employment, promoting independence and reintegration. | 1
2.6 | Engage employers to develop safe, supported employment opportunities with clear safeguarding expectations. | Year 2 Identify multi-agency pathways linking individuals to employment and training opportunities, with advocacy, mentoring, and tailored support to ensure safe and sustained participation. | Transition to Adulthood Sub-Group of the BFSB Employment and skills partners Jobcentre Plus Communiity and voluntary sector organisations | Increased number of individuals entering and sustaining employment or training, alongside positive feedback on safety, support, and confidence. | Individuals affected by exploitation access safe, appropriate employment or training, promoting independence and social reintegration. | 2
2.7 | Explore the provision of employability skills, advice and access to safeguarding support through youth hubs for young people transitioning to adulthood. | Year 1 Develop a multi-agency youth employment hub (physical or outreach). | Transition to Adulthood Sub-Group of the BFSB Employment and skills Communiity and voluntary sector organisations | Number/% of at-risk young people accessing hubs | Young people at risk of exploitation can access joined-up employment support and safeguarding in one trusted setting, improving engagement and safety. | 1
2.8 | Ensure consistent multi-agency processes to identify and respond to exploitation risk in young adults. | Year 1 Ensure that there is a clear, all-age exploitation risk identification and response protocol across police, local authority, health, and voluntary sector partners—aligned with existing safeguarding frameworks and thresholds. | Transition to Adulthood Sub-Group of the BFSB SVE Strategic Sub-Group of the CSP and BFSB | % of identified young adults at risk of exploitation who receive a multi-agency response within agreed timescales | Improved early identification and coordinated intervention reduces harm and prevalence of exploitation among young adults. | 1
2.9 | Review age-specific safeguarding pathways reflecting young adult development and legal status. | Year 1 Review existing children’s and adults’ safeguarding pathways to identify gaps, overlaps, and transition issues for young adults (18–25), including legal thresholds and service eligibility. | Transition to Adulthood Sub-Group of the BFSB BFC Children's Services - safeguarding lead BFC Adult Services - safeguarding lead | % of young adults (18–25) supported through a clearly defined and appropriate safeguarding pathway (audited for compliance). | Young adults receive proportionate, legally appropriate, and developmentally informed safeguarding responses, reducing risk of exploitation. | 1
2.1 | Ensure that there is current professional understanding of capacity, consent and lawful decision-making. | Year 1 Provide practical training on capacity, consent, and lawful decision-making (including application in exploitation contexts), using real case scenarios and legal frameworks. | Transition to Adulthood Sub-Group of the BFSB BFC Principal Social Worker | % of audited cases evidencing clear, lawful decision-making in relation to capacity and consent. | Professionals apply consistent, legally sound decisions, leading to more effective safeguarding and reduced risk of exploitation. | 1
2.11 | Provide access to safe, supported accommodation for young adults and prevent homelessness through early, coordinated intervention (linking into existing strategies: Homelessness and Rough Sleeping Strategy 2021-26, Housing Strategy 2024-29 and the Domestic Abuse Strategy 2026-32). | Ongoing | Transition to Adulthood Sub-Group of the BFSB BFC Housing and local housing providers | Number/% of at-risk young people accessing appropriate. | Improved housing stability and reduced exploitation risk. | 1
2.12 | Develop targeted awareness campaigns for young adults with exploitation risks and support. | Year 1 Work with young adults, including those with lived experience, to design relevant messaging on exploitation risks, healthy relationships, and how to access support. | Transition to Adulthood Sub-Group of the BFSB SVE Strategic Sub-Group of the CSP and BFSB | Reach and engagement levels of campaign among target young adult audiences (e.g. views, shares, event attendance, or service enquiries) | Increased awareness among young adults leads to earlier help-seeking and reduced vulnerability to exploitation. | 2
2.13 | Explore peer-led education initiatives supported by professionals. | Year 2: Partner with colleges, community organisations, and youth services to deliver regular peer-led education on exploitation risks, support pathways, and resilience-building. | Transition to Adulthood Sub-Group of the BFSB BFC Targeted Youth Support in conjunction with voluntary and community sector organisations. | Number of peer-led sessions delivered and % of participants reporting increased understanding of exploitation and support options. | Young adults are better informed and influenced by trusted peers, leading to increased resilience and earlier identification of exploitation risks. | 2
2.14 | Deliver digital literacy and online safety programmes addressing exploitation risks. | Year 2: Map current digital literacy and online safety programmes across partners, identify gaps relating to exploitation (e.g. grooming, coercion, financial exploitation), and agree priority cohorts. | Transition to Adulthood Sub-Group of the BFSB SVE Strategic Sub-Group of the CSP and BFSB | % of participants demonstrating increased knowledge of online exploitation risks and safe online behaviours (pre/post evaluation). | Young adults are more digitally resilient, reducing vulnerability to online exploitation and increasing safe help-seeking behaviours. | 2
2.15 | Improve access to timely, trauma-informed mental health support. | Year 1: Review current mental health services across statutory and voluntary sectors to identify gaps in timely access and trauma-informed support for those at risk of or experiencing exploitation. Establish clear, fast-track referral routes and prioritise trauma-informed interventions for high-risk individuals, ensuring alignment across safeguarding and mental health services. | Transition to Adulthood Sub-Group of the BFSB Health | Average waiting time from referral to access of trauma-informed mental health support for individuals at risk of exploitation. | Individuals receive timely, appropriate mental health support, improving recovery and reducing vulnerability to ongoing exploitation. | 1
2.16 | Provide targeted substance misuse support linked to safeguarding. | Year 1 Map and align substance misuse services with exploitation and safeguarding pathways to ensure joint working, shared risk assessment, and coordinated support for individuals at risk. Deliver targeted outreach and flexible, trauma-informed interventions for high-risk groups, including those experiencing exploitation, with clear referral routes between services. | Transition to Adulthood Sub-Group of the BFSB BFC New Hope (substance misuse services) | % of individuals identified at risk of exploitation who are assessed for substance misuse needs and receive appropriate support. | Reduced substance-related vulnerability contributes to decreased risk and impact of exploitation. | 1
2.17 | Strengthen the youth voice in service design and evaluation. | Year 2 Create forums (e.g. youth advisory panels, lived experience groups) with clear governance to regularly inform service design, delivery, and evaluation. Ensure young people are actively involved in shaping services, campaigns, and evaluations, with feedback loops demonstrating how their input influences decisions. | Transition to Adulthood Sub-Group of the BFSB BFC Targeted Youth Service in partnership with the CSP, BFSB and commissioned providers | % of relevant services evidencing youth input in design, commissioning, or evaluation processes. | Services are more responsive, accessible, and effective due to meaningful incorporation of young people’s voices. | 2
2.18 | Improve data collection and evaluation across transition services. | Year 1 Develop a consistent, multi-agency dataset for transition-age individuals (e.g. 16–25), including agreed definitions, indicators, and data-sharing protocols across children’s and adults’ services. Establish regular multi-agency data collection, analysis, and performance reporting to track transitions, identify risks, and inform service improvement. | Transition to Adulthood Sub-Group of the BFSB BFC Business Intelligence in partnership with the CSP and BFSB | % of partner agencies submitting complete and consistent transition data in line with the agreed dataset. | Improved data quality enables better understanding of need, more effective service planning, and reduced gaps in support during transition. | 1

## Perpetrators
All-age exploitation strategy 2026/31 - work plan
Priority 3: Perpetrators
Action No. | Action | Timescale | Lead | Success measure | Outcome | Year
3.1 | Deliver intelligence-led multi-agency enforcement activity focused on disruption and prevention. | Ongoing | TVP in conjunction with partners | Reduction in identified exploitation incidents, increased disruption activity (e.g., arrests, safeguarding interventions), and improved safety outcomes for victims. An increase in multi-agency supported intelligence operations. | Exploitation networks and high-risk activity are disrupted, reducing opportunities for harm and preventing further exploitation. | N/A
3.2 | Regularly review the current themed multi-agency groups addressing specific exploitation risks or locations. | Ongoing | SVE Strategic Sub-Group of the CSP and BFSB | Demonstrable reduction in incidents or risks within identified themes/locations and improved multi-agency coordination and response. | Targeted, coordinated interventions effectively reduce specific exploitation risks and address localised harm. | N/A
3.3 | Prioritise organisers, facilitators and repeat perpetrators for investigation. | Year 1 Establish joint operations between police, safeguarding teams, and partner agencies to focus resources on disrupting high-risk individuals, while ensuring victim safety and safeguarding. | TVP in conjunction with partners | Increase in successful investigations, arrests, and prosecutions of repeat perpetrators, alongside reduced victimisation in high-risk groups. | High-risk perpetrators are identified, disrupted, and held accountable, reducing ongoing and future exploitation. | 1
3.4 | Identify what existing perpetrator management frameworks are in place across partners. | Year 2 Bring partners together to agree consistent processes for risk assessment, monitoring, intervention, and information-sharing, with clear roles, responsibilities, and review mechanisms. | SVE Strategic Sub-Group of the CSP and BFSB | Improved consistency in perpetrator management across agencies, evidenced by coordinated interventions, reduced re-offending, and fewer safeguarding breaches. | All agencies work from a consistent, coordinated approach to managing perpetrators, reducing risk to victims and preventing reoffending. | 2
3.5 | Monitor levels of visible enforcement and disruption activity in identified hotspots. | Ongoing | TVP | Reduction in reported exploitation incidents in identified hotspots, increased community confidence, and measurable enforcement actions undertaken. | Exploitation activity is visibly disrupted in high-risk areas, improving community safety and reducing victimisation. | N/A
3.6 | Use criminal, civil and regulatory powers to disrupt perpetrator activity. | Ongoing | TVP Public Protection Partnership | Increase in successful use of criminal, civil, and regulatory interventions against perpetrators, with demonstrable reduction in exploitation incidents. | Perpetrator activity is actively disrupted using the full range of legal and regulatory powers, reducing opportunities for exploitation. | N/A
3.7 | Embed learning from cases and reviews into policy and practice. | Year 3 Update safeguarding policies, protocols, and staff training based on review outcomes, ensuring that lessons directly influence future practice across all agencies. | SVE Strategic Sub-Group of the CSP and BFSB | Demonstrable changes in policy, practice, or training resulting from case reviews, alongside improved multi-agency performance and reduced repeat incidents. | Services continuously improve, reducing risk and enhancing safeguarding responses based on evidence from real cases. | 3
3.8 | Ensure enforcement approaches are victim-centred and trauma-informed. | Ongoing | TVP Crown Prosecution Service | Positive feedback from victims on enforcement interactions, along with reduced reports of retraumatisation or disengagement from services. | Victims experience enforcement processes as safe, respectful, and supportive, reducing retraumatisation and encouraging engagement with services. | N/A
3.9 | Support safe relocation and protective measures for victims at ongoing risk. | Ongoing | TVP BFC Housing National Referral Mechanism (NRM) | Number of victims successfully relocated or provided with protective measures, with no subsequent incidents of re-exploitation. | Victims at ongoing risk are safely relocated and protected, reducing the likelihood of re-exploitation or harm. | N/A
3.1 | Use technology and digital investigations to disrupt online exploitation. | Ongoing | TVP | Increase in successful identification, intervention, and disruption of online exploitation cases, with measurable reductions in victim exposure. | Online exploitation is detected and disrupted promptly, reducing harm and protecting victims across all age groups. | N/A

## Support and Recovery
All-age exploitation strategy 2026/31 - work plan
Priority 4: Support and recovery
Action No. | Action | Timescale | Lead | Success measure | Outcome | Year
4.1 | Clarify and publicise access routes to support services across agencies. | Year 1 Map existing support services for children and adults across multi-agencies including referral routes, thresholds and eligibility criteria for each service. Highlight duplication, gaps and confusion points. | SVE Strategic Sub-Group of the CSP and BFSB | A clear multi-agency exploitation support pathway is developed, published, and embedded across partners, with increased practitioner awareness and improved access to support services evidenced through referral data and workforce feedback. | People at risk of, or experiencing, exploitation can more easily access the right support through clear, consistent referral routes across partner agencies. | 1
4.2 | Explore the strengthening of coordinated multi-agency recovery responses. | Year 2 Work with partners to explore a more coordinated approach to recovery support, including clear roles and referral pathways. | SVE Strategic Sub-Group of the CSP and BFSB | A multi-agency exploitation recovery framework is agreed and adopted by partner agencies, clearly setting out roles, responsibilities, and referral pathways for supporting victims/survivors. | Victims and survivors of exploitation receive more coordinated and consistent recovery support from partner agencies. | 2
4.3 | Explore personalised, trauma-informed recovery plans co-produced with victims. | Year 1 Work with safeguarding partners and specialist services to identify practical tools or templates to develop recovery plans. Ensure the framework is trauma-informed and victim-centred, with guidance on co-production, consent, and cultural sensitivity. | Children's Social Care Adult Social Care Specialist services | A trauma-informed recovery planning template is developed and agreed by partner agencies. | Victims and survivors receive personalised, trauma-informed recovery plans that reflect their needs and preferences. | 1
4.4 | Establish partnerships with specialist exploitation charities. | Year 2 Identify and engage priority specialist exploitation charities to agree roles, responsibilities, and collaboration mechanisms. | BFC Community Safety | Regular multi-agency contact and joint working is established with at least one specialist exploitation charity. | Victims and survivors benefit from timely access to specialist support through coordinated CSP collaboration. | 2
4.5 | Explore urgent and immediate access to safe emergency accommodation (linking into existing strategies: Homelessness and Rough Sleeping Strategy 2021-26, Housing Strategy 2024-29 and the Domestic Abuse Strategy 2026-32). | Year 1 Identify and catalogue existing emergency housing and safe spaces for children and adults at risk of exploitation. Establish agreed points of contact within housing providers, shelters, and local authority services to prioritise urgent placements. | BFC Housing Local housing providers Emergency housing providers and specialist support charities | Frontline staff can place at-risk children and adults into emergency accommodation within 24 hours of identification. | Victims and survivors have immediate access to safe, secure spaces, reducing risk and supporting early recovery. | 1
4.6 | Explore availability of long-term supported housing (linking into existing strategies: Homelessness and Rough Sleeping Strategy 2021-26, Housing Strategy 2024-29 and the Domestic Abuse Strategy 2026-32). | Year 2 Identify current long-term housing options for victims/survivors of exploitation (children and adults). Assess capacity, suitability, and gaps in meeting the needs of different age groups and risk levels. | BFC Housing Local housing providers | An agreed plan with housing partners is in place to increase the availability of long-term supported housing for exploitation victims/survivors. | Victims and survivors have access to stable, supported housing, enabling sustained recovery and reduced risk of re-exploitation. | 2
4.7 | Ensure services are culturally appropriate and inclusive. | Year 1 Analyse local exploitation data by protected characteristics (e.g. ethnicity, gender, disability, age) to identify disproportionality, unmet need, and gaps in service access or outcomes. | SVE Strategic Sub-Group of the CSP and BFSB | Increase in the proportion of referrals, service uptake, and positive outcomes from identified underrepresented groups (e.g. improved representation in data compared to local population demographics). | Services are culturally appropriate and accessible, leading to increased engagement from underrepresented and marginalised groups affected by exploitation. | 1
4.8 | Explore access to legal advice and advocacy. | Year 2 Identify existing legal advice and advocacy services (including specialist exploitation, immigration, and youth advocacy). | SVE Strategic Sub-Group of the CSP and BFSB | Increase in the number and timeliness of referrals to legal advice and advocacy services, alongside positive feedback from service users on accessibility and support received. | Victims of exploitation (all ages) can access timely, appropriate legal advice and advocacy, improving protection, rights awareness, and engagement with services. | 2
4.9 | Identify and ensure pathways are in place to trauma-informed mental health support. | Year 1 Ensure frontline staff across partner agencies have access to trauma-informed practice training. | Health | Increased access to and uptake of trauma-informed mental health services, with improved service user outcomes and feedback. | Victims of exploitation receive timely, trauma-informed mental health support that improves wellbeing and engagement with services. | 1
4.1 | Explore peer support networks with appropriate safeguards. | Year 2 Work with survivors and community groups to design peer support that is culturally appropriate, age-inclusive, and responsive to different exploitation experiences. | Voluntary and community sector organisations | Number of individuals accessing peer support and reporting increased wellbeing, safety, and sense of support, alongside no/low safeguarding incidents within the provision. | Safe, inclusive peer support networks improve connection, trust, and recovery for individuals affected by exploitation. | 2
4.11 | Improve access to physical healthcare through advocacy and coordination. | Year 1 Identify gaps in access to physical healthcare (e.g. GP registration, sexual health, emergency care) for those affected by exploitation, including barriers linked to culture, language, or trust. | Health | Increased registration with primary care and uptake of relevant health services, alongside reduced missed appointments and improved service user feedback on access. | Individuals affected by exploitation can access timely, appropriate physical healthcare, improving health and safeguarding outcomes. | 1
4.12 | Support community reintegration through education, training and employment. | Year 1 Assess local education, training, and employment provision to identify gaps and barriers for those affected by exploitation (e.g. stigma, criminal records, disrupted education, immigration status). | Education providers Department for Work and Pensions Probation and Youth Justice Services Voluntary and community sector organisations | Increased number of individuals entering and sustaining education, training, or employment, alongside improved confidence and stability reported by service users. | Individuals affected by exploitation are supported to access and sustain education, training, or employment, promoting independence and reintegration. | 1
4.13 | Deliver life skills, english for speakers of other languages (ESOL) and education programmes. | Year 2 Identify the specific life skills, ESOL, and education needs of individuals affected by exploitation and map existing local programmes, including gaps for different age groups and language needs. | BFC Education BFC Learning and Achievement Other learning partners | Increased participation and completion rates in life skills, ESOL, and education programmes, alongside improved confidence and self-reported capability. | Individuals affected by exploitation gain essential life skills, language proficiency, and educational support, improving independence and engagement with services. | 2
4.14 | Support access to safe and appropriate employment and training. | Year 2 Identify multi-agency pathways linking individuals to employment and training opportunities, with advocacy, mentoring, and tailored support to ensure safe and sustained participation. | Employment and skills partners Jobcentre Plus Communiity and voluntary sector organisations | Increased number of individuals entering and sustaining employment or training, alongside positive feedback on safety, support, and confidence. | Individuals affected by exploitation access safe, appropriate employment or training, promoting independence and social reintegration. | 2
4.15 | Provide long-term follow-up support to reduce re-exploitation risk. | Year 3 Create structured follow-up pathways with clear responsibilities, regular check-ins, and multi-agency collaboration to provide sustained support and quickly respond to emerging risks. | Children's Social Care Adult Social Care Specialist services | Reduction in repeat exploitation cases and sustained engagement with support services over 6–12 months. | Individuals affected by exploitation receive ongoing, tailored support, reducing the likelihood of re-exploitation and promoting long-term stability. | 3
4.16 | Embed lived experience into evaluation and service improvement. | Year 2 Develop mechanisms (e.g., surveys, focus groups, case reviews) to capture lived experience insights and embed them into service evaluation, performance monitoring, and strategy updates. | SVE Strategic Sub-Group of the CSP and BFSB | Evidence of service changes and improvements directly informed by lived experience input, alongside positive feedback from participants on being heard and influencing services. | Services are continuously improved based on real-world experiences, increasing relevance, accessibility, and effectiveness for those affected by exploitation. | 2